## BP
Milestone | Sub-Milestone | Activities | Activity Code | Key Milestones Flag | Target Start Date-Aggressive | Target Start Date - Realistic | Duration-Aggressive | Duration - Realistic | Target Finish Date - Aggressive | Target Finish Date - Realistic | Actual Start Date | Actual Completion Date | Status | POC | Remark
Contract formalization | Issue of allottment letter | Agreement Signing | A1 | 1 |  |  |  |  | 2023-06-08 | 2023-06-08 |  | 2023-06-08 | Completed | PPD
Preliminery activities | DGPS Survey | Appointment of DGPS Survey agency | P1 |  |  |  | 5 | 10 | 2023-07-25 | 2023-08-01 |  |  | In-progress | Piyush Shah
Preliminery activities | DGPS Survey | DGPS Survey | P2 | 1 |  |  | 75 | 90 | 2023-10-08 | 2023-10-30 |  |  | Yet to start | Piyush Shah
Preliminery activities | Collection of Cadestral Map,revenue records etc | Collection of Cadestral Map,revenue records etc | P3 |  |  |  | 30 | 45 | 2023-08-24 | 2023-09-15 |  |  | Yet to start | Piyush Shah / CPD
Preliminery activities | Digitization of Map | Digitization of Map | P4 |  |  |  | 65 | 80 | 2023-09-28 | 2023-10-20 |  |  | Yet to start | Piyush Shah / CPD
Preliminery activities | Collection of GR from CMPDI | Collection of GR from CMPDI- Softcopy | P5 | [5 empty] | 2023-07-13 | 2023-07-13 |  |  | Completed | Piyush Shah
Preliminery activities | Collection of GR from CMPDI | Collection of GR from CMPDI-Hardcopy | P6 | 1 |  |  | 14 | 21 | 2023-07-27 | 2023-08-03 |  |  | Yet to start | CPD
Mining Plan & Mine closure Plan | Regiter in SWCS Portal | Nominate Authorized Personnel | MP1 | [5 empty] | 2023-06-08 | 2023-06-08 |  |  | Completed | PPD
Mining Plan & Mine closure Plan | Regiter in SWCS Portal | Register in SWCS portal (Authorised Personnel) | MP2 | [5 empty] | 2023-07-10 | 2023-07-10 |  |  | Completed | PPD
Mining Plan & Mine closure Plan | Regiter in SWCS Portal | Obtain Login Credentials | MP3 | 1 |  |  |  |  | 2023-07-17 | 2023-07-17 |  |  | Completed | PPD
Mining Plan & Mine closure Plan | Internal Review of Coal Mining Plan | Submission of draft mine plan to GMDC by third party consultant | MP4 | 1 |  |  | 35 | 45 | 2023-08-29 | 2023-09-11 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Internal Review of Coal Mining Plan | Expert Reviewer's comments incorporation | MP5 |  |  |  | 4 | 10 | 2023-09-02 | 2023-09-21 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Internal Review of Coal Mining Plan | Pre-check from Expert reviewer before submission | MP6 |  |  |  | 2 | 5 | 2023-09-04 | 2023-09-26 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Internal Review of Coal Mining Plan | Addressal of Expert Reviewer's comments | MP7 |  |  |  | 2 | 5 | 2023-09-06 | 2023-10-01 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Internal Review of Coal Mining Plan | Re-sharing the draft after addressing the comments | MP8 |  |  |  | 1 | 2 | 2023-09-07 | 2023-10-03 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Internal Review of Coal Mining Plan | Go ahead from GMDC | MP9 |  |  |  | 1 | 2 | 2023-09-08 | 2023-10-05 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Submission of Coal Mining Plan | Submission of reviewed Mining plan in the portal | MP10 | 1 |  |  | 2 | 4 | 2023-09-10 | 2023-10-09 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Submission of Coal Mining Plan | Scrutiny comments from MoC | MP11 |  |  |  | 15 | 21 | 2023-09-25 | 2023-10-30 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Submission of Coal Mining Plan | Addressal of scrutiny comments from MoC | MP12 |  |  |  | 2 | 5 | 2023-09-27 | 2023-11-04 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Submission of Coal Mining Plan | Final copies submission after addressing the comments | MP13 |  |  |  | 2 | 2 | 2023-09-29 | 2023-11-06 |  |  | Yet to start | PPD + GEO
Mining Plan & Mine closure Plan | Approval of mining plan by MoC | Approval of mining plan by MoC | MP14 | 1 |  |  | 15 | 15 | 2023-10-14 | 2023-11-21 |  |  | Yet to start | PPD + GEO
Forest Clearance | Forest clearance | Prepare Form A for online registration of Forest Diversion proposal | FC1
Forest Clearance |  | Scrutiny at APCCF Office and Approval of online proposal | FC2
Forest Clearance |  | Submit Physical copy of Application to DFO | FC3
Forest Clearance |  | Processing of Forest Proposal as per Checklist by DFO | FC4
Forest Clearance |  | DFO Review and forwards the proposal to CF | FC5
Forest Clearance |  | CF/CCF Reviews of PART II Documents | FC6
Forest Clearance |  | CF/ CCF inspection of Site | FC7
Forest Clearance |  | CF/CCF rocommendation for PART III | FC8
Forest Clearance |  | APCCF Reviews PART III | FC9
Forest Clearance |  | APCCF recommend Part IV to PCCF | FC10
Forest Clearance |  | PCCF recommend Part IV to Secretary (Forest) | FC11
Forest Clearance |  | Secretory (Forest) Reviews of PART IV | FC12
Forest Clearance |  | Secretory seeks approval from state forest minister | FC13
Forest Clearance |  | Secretary Forest recommends Part V to MoEF | FC14
Forest Clearance |  | MoEF Reviews Part V | FC15
Forest Clearance |  | MoEF Directs regional MoEF for site inspection | FC16
Forest Clearance |  | Site Inspection and Report Submission by Regional MoEF | FC17
Forest Clearance |  | Presentation to FAC | FC18
Forest Clearance |  | FAC recommends the proposal to MoEF for Stage-1 | FC19
Forest Clearance |  | FC Stage I Approval from MoEF | FC20
Forest Clearance |  | APCCF seeks FC I compliance from DFO/ CF/CCF | FC21
Forest Clearance |  | DFO raises demand note for NPV, CA Scheme | FC22
Forest Clearance |  | Submit payment against demand note | FC23
Forest Clearance |  | Submit FC I compliance report to DFO | FC24
Forest Clearance |  | DFO reviews& forwards compliance report to CF/CCF | FC25
Forest Clearance |  | CF/CCF reviews& forwards Compliance report to PCCF | FC26
Forest Clearance |  | PCCF reviews& forward compliance report to Secretory (Forest) | FC27
Forest Clearance |  | Secretory (Forest) reviews& forward compliance report to MoEF | FC28
Forest Clearance |  | DGPS Survey of Complete Area | FC29
Forest Clearance |  | Grant of Forest Clearance from State | FC30
Forest Clearance | Forest Right (FRA NOC) | Submission of application to Collector to start the FRA Process | FRA1
Forest Clearance |  | Collector advises SDM/Tehsildar to start the FRA Process | FRA2
Forest Clearance |  | Conduct of Gram Sabha at each Village /report of Sarpanch/secretary of grampanchayat for FRA consent | FRA3
Forest Clearance |  | Gram Sabha Resolution and NOC from Village level (FRC) along with the list of Claimant | FRA4
Forest Clearance |  | Proposal forwarded to Sub Divisional Level Committee through Tehsildar along with report | FRA5
Forest Clearance |  | Recommendation from Sub Division Level (Forest Rights) Committee | FRA6
Forest Clearance |  | Recommendation from District Level Committee Consist of Collector, DFO, Asst. Commissioner (Tribal Development) | FRA7
Forest Clearance |  | District level committee issue Forest Rights Certificates | FRA8
Forest Clearance |  | Grant of FRA NOC by Collector | FRA9
Forest Clearance | Compensatory Afforestation | Identification of CA Land (Revenue Govt. Land/ Revenue Forest Land) | CA1
Forest Clearance |  | Application to Collector for NOC for CA Land | CA2
Forest Clearance |  | Conduct Gram Sabh in concerned villages | CA3
Forest Clearance |  | Obtain NoC from Collector | CA4
Forest Clearance |  | Completion of DGPS Survey for CA Land | CA5
Forest Clearance |  | Submission of DGPS report to DFO/ Checking of DSS System | CA6
Forest Clearance |  | Suitability Certificate from DFO/CCF | CA7
Forest Clearance |  | Preparation of CA Scheme | CA8
Forest Clearance |  | Approval of CA Scheme (Technical Vetting by CF/CCF) | CA9
Forest Clearance |  | Application for Transfer and mutation of CA Land to Collector | CA10
Forest Clearance |  | Collector directs SDM/Tehsildar to submit report on the land | CA11
Forest Clearance |  | SDM/ Tehsildar recommends to collector for mutation of the land | CA12
Forest Clearance |  | Collector Directs SDM/Tehsildar complete the mutation process | CA13
Forest Clearance | Tree Enumeration | Letter from DFO to FMIS for Grid Maps, Stock Maps etc. | TE1
Forest Clearance |  | Letter from FMIS for Demand Note for the Cost of Maps | TE2
Forest Clearance |  | Depositing Fees at FMIS for maps | TE3
Forest Clearance |  | Issue of Grid Maps, Stock Maps by FMIS | TE4
Forest Clearance |  | DFO forwards letter to ROs for formation of Tree Enemuration Commi | TE5
Forest Clearance |  | RO form the committe for tree enemuration | TE6
Forest Clearance |  | Mobilization of Tree Enumeration committes (Starting of Tree enumer | TE7
Forest Clearance |  | Tree Enumeration report preprared by committee and forwards to DF | TE8
Forest Clearance |  | DFO Review and approves the report | TE9
Forest Clearance |  | Tree Enumeration Completed | TE10
Forest Clearance | Wild Life Conservation Plan (WLCP) | Preparation and Submission of WLCP to DFO | WLCP1
Forest Clearance |  | DGPS Survey of Complete Area | WLCP2
Forest Clearance |  | CF/CCF recommend the WLCP to Chief Wild Life Warden (CWLW) | WLCP3
Forest Clearance |  | Approval of WLCP by State Govt.(Chief Wild Life Warden) | WLCP4
Forest Clearance | Forest Land Tree Felling and Physical Possession | Application for Tree Felling Permission to DFO | TFPP1
Forest Clearance |  | DFO Issues letter to Forest Ranger for tree enumeration | TFPP2
Forest Clearance |  | DFO issue the marking hammer to Ranger officer | TFPP3
Forest Clearance |  | Range officer directs deputy ranger to start Enumeration | TFPP4
Forest Clearance |  | Deputy ranger submit tree enumeration list to Ranger | TFPP5
Forest Clearance |  | Ranger submit enemuration list to SDO | TFPP6
Forest Clearance |  | SDO Submit enemuration list to DFO | TFPP7
Forest Clearance |  | DFO recommend application to APCCF Production | TFPP8
Forest Clearance |  | APCCF Production approves tree felling permission to DFO | TFPP9
Forest Clearance |  | DFO estimates cost of tree felling | TFPP10
Forest Clearance |  | DFO raises the demand note to user agency | TFPP11
Forest Clearance |  | User agency makes payment against demand note | TFPP12
Forest Clearance |  | DFO permits ranger to start tree felling | TFPP13
Forest Clearance |  | Ranger writes to DFO to issue Tree Felling Hammer | TFPP14
Forest Clearance |  | DFO issues Tree felling hammer to Ranger | TFPP15
Forest Clearance |  | Ranger start tree felling,debarking logging, and transporting | TFPP16
Forest Clearance |  | Tree Felling for ha | TFPP17
Forest Clearance |  | User Agency submit application to DFO for taking the posession of felled area with coordinates of same area | TFPP18
Forest Clearance |  | DFO Grants permission after field visits by ranger (regular) | TFPP19
Environment Clearance | Environment Clearance | Preparation of Prefeasibility Report/Form 1 | EC1 | [5 empty] | 2023-10-15 | 2023-11-20
Environment Clearance |  | On line Submission of Form 1& Prefeasibility Report | EC2
Environment Clearance |  | ToR presentation to EAC | EC3
Environment Clearance |  | ToR Granted by MoEF | EC4
Environment Clearance |  | Acceptance/seek amendment | EC5
Environment Clearance |  | Baseline Study | EC6
Environment Clearance |  | Hydrogeological Investigation | EC7
Environment Clearance |  | GW Modeling (Depends on ToR) | EC8
Environment Clearance |  | Draft EIA/EMP preparation | EC9
Environment Clearance |  | EIA/EMP Report submission to Member Secretary, SPCB for PH | EC10
Environment Clearance |  | Notice for Public Hearing by SPCB | EC11
Environment Clearance |  | Conducting Public Hearing | EC12
Environment Clearance |  | SPCB Recommendation of public hearing proceeding to MoEF | EC13
Environment Clearance |  | Preparation of revised EIA/EMP on the basis of Public Hearing MoM | EC14
Environment Clearance |  | Final EIA/ EMP Submission to MoEF | EC15
Environment Clearance |  | Review of EIA/EMP by MoEF | EC16
Environment Clearance |  | Issue of Date for EC Presentation | EC17
Environment Clearance |  | EIA/EMP Presentation to MoEF | EC18
Environment Clearance |  | Grant of Environment Clearance by MoEF | EC19
Mining Lease | Mining Lease | Prepare and Submit application for Mining Lease to District Collector/ District Mining Officer | ML1
Mining Lease |  | DGPS Survey of Complete Area | ML2
Mining Lease |  | Obtain NoC from Tehsildar/ DFO/ Gram Panchayats | ML3
Mining Lease |  | Collector recommends the application to Director Geology and Mining (DGM) | ML4
Mining Lease |  | DGM forwards to Secretary MRD (Mineral Resource Department) | ML5
Mining Lease |  | Secretary MRD recommend for prior approval to Central Govt. (Mo | ML6
Mining Lease |  | Issuance of Prior Approval by Central Government (MoC) | ML7
Mining Lease |  | State MRD issues a letter for necessary approval to user agency | ML8
Mining Lease |  | User agency submit the necessary approvals and request for grant o | ML9
Mining Lease |  | Secretary, MRD Grant ML to user agency | ML10
Mining Lease |  | User Agency submit applilcation to collector for execution of ML | ML11
Mining Lease |  | Execute Mining Lease | ML12
Land Acquisition and R & R | Land Acquisition (LARR Act 2013) | Apply to DC u/s 2 (1) of LARR Act, 2013 | LA1
Land Acquisition and R & R |  | Preliminary investigation for determination of Social Impact& Public Purpose U/S 4(1) | LA2
Land Acquisition and R & R |  | Issue of Notice by DC for SIA Study u/s 4(1) | LA3
Land Acquisition and R & R |  | Make 4(1) notification available to Panchayat, Muncipality, DC, SDM | LA4
Land Acquisition and R & R |  | Publish 4(1) notification in affected area | LA5
Land Acquisition and R & R |  | Payment for SIA to DC | LA6
Land Acquisition and R & R |  | Start of Social Impact Assessment Study | LA7
Land Acquisition and R & R |  | Preparation of SIA/SMP | LA8
Land Acquisition and R & R |  | Publicity of Public Hearing u/s 5 | LA9
Land Acquisition and R & R |  | SIA Public Hearing u/s 5 | LA10
Land Acquisition and R & R |  | Preparation of Final SIA/SMP u/s sec 5 | LA11
Land Acquisition and R & R |  | Translation of SIA/SMP in Local Language | LA12
Land Acquisition and R & R |  | Publish SIA/SMP in local Language to Panchayat, Municipality, DC,SDM, Tehsil | LA13
Land Acquisition and R & R |  | Recommendation by Expert Group u/s 7(6) | LA14
Land Acquisition and R & R |  | Make Recommendation available (in Local Language) to Panchayat, Muncipality, DC, SDM,Tehsil | LA15
Land Acquisition and R & R |  | Examination of LA Proposal& SIA/SMP by Govt u/s 8 | LA16
Land Acquisition and R & R |  | Decision of Govt for LA u/s 8(1) | LA17
Land Acquisition and R & R |  | Govt Decision to be made available to Panchayat,Muncipality, DC, SDM,Tehsil u/s 8(3) | LA18
Land Acquisition and R & R |  | Demand Note for compensation and Service Charges | LA19
Land Acquisition and R & R |  | Deposit of money against demand note | LA20
Land Acquisition and R & R |  | Publication of Priliminary Notification u/s11 (1) | LA21
Land Acquisition and R & R |  | Publication in two daily newspaper, Panchayat, District collector, SDM and Tehsil (Local Language) | LA22
Land Acquisition and R & R |  | Publish 11 (1) in affected area (in Local Language) | LA23
Land Acquisition and R & R |  | Informed concerned Gram Sabha, Muncipality u/s 11(2) | LA24
Land Acquisition and R & R |  | Updation of Land Record by Collector u/s 11(5) | LA25
Land Acquisition and R & R |  | DGPS Survey of Complete Area | LA26
Land Acquisition and R & R |  | Payment for damage during survey u/s 13 | LA27
Land Acquisition and R & R |  | Hearing of objection u/s 15 (1) | LA28
Land Acquisition and R & R |  | Prepare& submit Draft R&R Scheme u/s 16 (u/s 43) | LA29
Land Acquisition and R & R |  | R&R Scheme Prepared by R&R Administrator | LA30
Land Acquisition and R & R |  | Publicity of Draft R&R Scheme in affected areas | LA31
Land Acquisition and R & R |  | Notice for Public Hearing for R&R u/s 16(5) | LA32
Land Acquisition and R & R |  | Conduct Public Hearing/ Gram Sabha in each village u/s 16(5) | LA33
Land Acquisition and R & R |  | Submit Draft R&R Scheme to Collector u/s 16(6) | LA34
Land Acquisition and R & R |  | Review of Draft R&R Scheme by collector and submission to Commissioner u/s 17(1) | LA35
Land Acquisition and R & R |  | Approval of R&R scheme by Commissioner u/s 17(2) | LA36
Land Acquisition and R & R |  | Publish Approved R&R Scheme in affected area u/s 18 | LA37
Land Acquisition and R & R |  | Deposit amount in full or part as prescribed | LA38
Land Acquisition and R & R |  | Publication of Declaration and Summary of R&R by Secretary to gov | LA39
Land Acquisition and R & R |  | Land Declared u/s 19 (LA 2013) | LA40
Land Acquisition and R & R |  | Mark and measure the land u/s 20 | LA41
Land Acquisition and R & R |  | Notice to Person interested u/s 21 | LA42
Land Acquisition and R & R |  | Hearing of Objections u/s 21 (2) | LA43
Land Acquisition and R & R |  | Enquiry& Land acquisition award by collector u/s 23 | LA44
Land Acquisition and R & R |  | Payment of balance amount to Govt. | LA45
Land Acquisition and R & R |  | Payment Disbursement | LA46
Land Acquisition and R & R |  | Possession of Land u/s 38 | LA47
Land Acquisition and R & R |  | R&R Award by collector for PAFs u/s 31(1) | LA48
Land Acquisition and R & R |  | Constitute R&R committe of Project u/s 45 to monitor and review of progress of R&R | LA49
Land Acquisition and R & R |  | Quantify and deposit R&R Amount into a account as directed by R&R Administrator u/s 47 | LA50
Other Consent and Clearances | Consent to Establish | Application by Project Proponent on online portal | CTE1 |  |  |  | 0
Other Consent and Clearances | Consent to Establish | Submission of Hard Copy to Member Secretary, SPCB along with the online communication | CTE2 |  |  |  | 7
Other Consent and Clearances | Consent to Establish | Site Inspection by RO, SPCB& its recommendations | CTE3 |  |  |  | 15
Other Consent and Clearances | Consent to Establish | Presentation and Appraisal by Technical Committee | CTE4 |  |  |  | 15
Other Consent and Clearances | Consent to Establish | Grant of CTE | CTE5 |  |  |  | 23
Other Consent and Clearances | Consent to Establish | Payment of requisite fees by Project Proponenent | CTE6
Other Consent and Clearances | Consent to Operate | Application by Project Proponent on online portal | CTO1 |  |  |  | 0
Other Consent and Clearances | Consent to Operate | Submission of Hard Copy to Member Secretary, SPCB along with the online communication | CTO2 |  |  |  | 7
Other Consent and Clearances | Consent to Operate | Site Inspection by RO, SPCB& its recommendations | CTO3 |  |  |  | 15
Other Consent and Clearances | Consent to Operate | Presentation and Appraisal by Technical Committee | CTO4 |  |  |  | 15
Other Consent and Clearances | Consent to Operate | Grant of CTO | CTO5 |  |  |  | 23
Ground breaking + Mine Operationalization | DGPS Survey of Complete Area | DGPS Survey of Complete Area | MO1
Ground breaking + Mine Operationalization | Application for Mine Opening to Coal Controller | Grant of Mine Opening Permission | MO2
Ground breaking + Mine Operationalization | Application to DGMS for necessary permissions | Permission for Deployment of HEMM | MO3
Ground breaking + Mine Operationalization | Application to CLC | Permission for deployment of contract labour | MO4
Ground breaking + Mine Operationalization | Notice regarding industrial unit | Notice regarding industrial unit | MO5
Ground breaking + Mine Operationalization | Opening of Escrow Account | Opening of Escrow Account | MO6
Ground breaking + Mine Operationalization | Mine Operation | Notice to DGMS regarding Mine opening | MO7
Ground breaking + Mine Operationalization | Intimation of actual date of start of mine to DGMS and Collector | Intimation of actual date of start of mine to DGMS and Collector | MO8
Ground breaking + Mine Operationalization | Start of Box cut | Start of Box cut | MO9
Formulas:
Target Finish Date - Aggressive = [Target Finish Date - Aggressive, row above]+[Duration-Aggressive]
Target Finish Date - Aggressive = J4+[Duration-Aggressive]
Target Finish Date - Realistic = [Target Finish Date - Realistic, row above]+[Duration - Realistic]
Target Finish Date - Realistic = K4+[Duration - Realistic]

## BW_ (hidden)
Milestone | Sub-Milestone | Activities | Activity Code | Key Milestones Flag | Target Start Date | Target Finish Date - Aggressive | Target Finish Date - Realistic | Duration | Actual Start Date | Actual Completion Date | Status | POC | Remark
1-Contract formalization | Issue of allottment letter | Agreement Signing | A-1 | [7 empty] | Completed | PPD
2- Preliminery activities | DGPS Survey
Collection of Cadestral Map,revenue records etc
Digitization of Map
3-Mining Plan & Mine closure Plan | Regiter in SWCS Portal | Nominate Authorized Personnel | MP1 | [7 empty] | Completed | PPD
| Regiter in SWCS Portal | Register in SWCS portal (Authorised Personnel) | MP2 | [7 empty] | Completed | PPD
| Regiter in SWCS Portal | Obtain Login Credentials | MP3 | 1 |  | 2023-07-14 | 2023-07-21 |  |  |  | In-progress | PPD
| Internal Review of Coal Mining Plan | Submission of draft mine plan to GMDC by third party consultant | MP4 |  |  | 2023-08-28 | 2023-10-01 |  |  |  |  | PPD + GEO
| Internal Review of Coal Mining Plan | Expert Reviewer's comments incorporation | MP5 |  |  | 2023-09-02 | 2023-10-04 |  |  |  |  | PPD + GEO
| Internal Review of Coal Mining Plan | Pre-check from Expert reviewer before submission | MP6 |  |  | 2023-09-04 | 2023-10-07 |  |  |  |  | PPD + GEO
| Internal Review of Coal Mining Plan | Addressal of Expert Reviewer's comments | MP7 |  |  | 2023-09-11 | 2023-10-10 |  |  |  |  | PPD + GEO
| Internal Review of Coal Mining Plan | Re-sharing the draft after addressing the comments | MP8 |  |  | 2023-09-13 | 2023-10-15 |  |  |  |  | PPD + GEO
| Internal Review of Coal Mining Plan | Go ahead from GMDC | MP9 |  |  | 2023-09-18 | 2023-10-20 |  |  |  |  | PPD + GEO
| Submission of Coal Mining Plan | Submission of reviewed Mining plan in the portal | MP10 | 1 |  | 2023-09-20 | 2023-10-23 |  |  |  |  | PPD + GEO
| Submission of Coal Mining Plan | Scrutiny comments from MoC | MP11 |  |  | 2023-10-11 | 2023-11-13 |  |  |  |  | PPD + GEO
| Submission of Coal Mining Plan | Addressal of scrutiny comments from MoC | MP12 |  |  | 2023-10-16 | 2023-11-20 |  |  |  |  | PPD + GEO
| Submission of Coal Mining Plan | Final copies submission after addressing the comments | MP13 |  |  | 2023-10-21 | 2023-11-22 |  |  |  |  | PPD + GEO
| Approval of mining plan by MoC | Approval of mining plan by MoC | MP14 | 1 |  | 2023-11-20 | 2023-12-22 |  |  |  |  | PPD + GEO
4-Forest Clearance & Environment Clearance | Forest clearance | Prepare Form A for online registration of Forest Diversion proposal | FC1
|  | Scrutiny at APCCF Office and Approval of online proposal | FC2
|  | Submit Physical copy of Application to DFO | FC3
|  | Processing of Forest Proposal as per Checklist by DFO | FC4
|  | DFO Review and forwards the proposal to CF | FC5
|  | CF/CCF Reviews of PART II Documents | FC6
|  | CF/ CCF inspection of Site | FC7
|  | CF/CCF rocommendation for PART III | FC8
|  | APCCF Reviews PART III | FC9
|  | APCCF recommend Part IV to PCCF | FC10
|  | PCCF recommend Part IV to Secretary (Forest) | FC11
|  | Secretory (Forest) Reviews of PART IV | FC12
|  | Secretory seeks approval from state forest minister | FC13
|  | Secretary Forest recommends Part V to MoEF | FC14
|  | MoEF Reviews Part V | FC15
|  | MoEF Directs regional MoEF for site inspection | FC16
|  | Site Inspection and Report Submission by Regional MoEF | FC17
|  | Presentation to FAC | FC18
|  | FAC recommends the proposal to MoEF for Stage-1 | FC19
|  | FC Stage I Approval from MoEF | FC20
|  | APCCF seeks FC I compliance from DFO/ CF/CCF | FC21
|  | DFO raises demand note for NPV, CA Scheme | FC22
|  | Submit payment against demand note | FC23
|  | Submit FC I compliance report to DFO | FC24
|  | DFO reviews& forwards compliance report to CF/CCF | FC25
|  | CF/CCF reviews& forwards Compliance report to PCCF | FC26
|  | PCCF reviews& forward compliance report to Secretory (Forest) | FC27
|  | Secretory (Forest) reviews& forward compliance report to MoEF | FC28
|  | DGPS Survey of Complete Area | FC29
|  | Grant of Forest Clearance from State | FC30
| Forest Right (FRA NOC) | Submission of application to Collector to start the FRA Process | FRA1
|  | Collector advises SDM/Tehsildar to start the FRA Process | FRA2
|  | Conduct of Gram Sabha at each Village /report of Sarpanch/secretary of grampanchayat for FRA consent | FRA3
|  | Gram Sabha Resolution and NOC from Village level (FRC) along with the list of Claimant | FRA4
|  | Proposal forwarded to Sub Divisional Level Committee through Tehsildar along with report | FRA5
|  | Recommendation from Sub Division Level (Forest Rights) Committee | FRA6
|  | Recommendation from District Level Committee Consist of Collector, DFO, Asst. Commissioner (Tribal Development) | FRA7
|  | District level committee issue Forest Rights Certificates | FRA8
|  | Grant of FRA NOC by Collector | FRA9
| Compensatory Afforestation | Identification of CA Land (Revenue Govt. Land/ Revenue Forest Land) | CA1
|  | Application to Collector for NOC for CA Land | CA2
|  | Conduct Gram Sabh in concerned villages | CA3
|  | Obtain NoC from Collector | CA4
|  | Completion of DGPS Survey for CA Land | CA5
|  | Submission of DGPS report to DFO/ Checking of DSS System | CA6
|  | Suitability Certificate from DFO/CCF | CA7
|  | Preparation of CA Scheme | CA8
|  | Approval of CA Scheme (Technical Vetting by CF/CCF) | CA9
|  | Application for Transfer and mutation of CA Land to Collector | CA10
|  | Collector directs SDM/Tehsildar to submit report on the land | CA11
|  | SDM/ Tehsildar recommends to collector for mutation of the land | CA12
|  | Collector Directs SDM/Tehsildar complete the mutation process | CA13
| Tree Enumeration | Letter from DFO to FMIS for Grid Maps, Stock Maps etc. | TE1
|  | Letter from FMIS for Demand Note for the Cost of Maps | TE2
|  | Depositing Fees at FMIS for maps | TE3
|  | Issue of Grid Maps, Stock Maps by FMIS | TE4
|  | DFO forwards letter to ROs for formation of Tree Enemuration Commi | TE5
|  | RO form the committe for tree enemuration | TE6
|  | Mobilization of Tree Enumeration committes (Starting of Tree enumer | TE7
|  | Tree Enumeration report preprared by committee and forwards to DF | TE8
|  | DFO Review and approves the report | TE9
|  | Tree Enumeration Completed | TE10
| Wild Life Conservation Plan (WLCP) | Preparation and Submission of WLCP to DFO | WLCP1
|  | DGPS Survey of Complete Area | WLCP2
|  | CF/CCF recommend the WLCP to Chief Wild Life Warden (CWLW) | WLCP3
|  | Approval of WLCP by State Govt.(Chief Wild Life Warden) | WLCP4
| Forest Land Tree Felling and Physical Possession | Application for Tree Felling Permission to DFO | TFPP1
|  | DFO Issues letter to Forest Ranger for tree enumeration | TFPP2
|  | DFO issue the marking hammer to Ranger officer | TFPP3
|  | Range officer directs deputy ranger to start Enumeration | TFPP4
|  | Deputy ranger submit tree enumeration list to Ranger | TFPP5
|  | Ranger submit enemuration list to SDO | TFPP6
|  | SDO Submit enemuration list to DFO | TFPP7
|  | DFO recommend application to APCCF Production | TFPP8
|  | APCCF Production approves tree felling permission to DFO | TFPP9
|  | DFO estimates cost of tree felling | TFPP10
|  | DFO raises the demand note to user agency | TFPP11
|  | User agency makes payment against demand note | TFPP12
|  | DFO permits ranger to start tree felling | TFPP13
|  | Ranger writes to DFO to issue Tree Felling Hammer | TFPP14
|  | DFO issues Tree felling hammer to Ranger | TFPP15
|  | Ranger start tree felling,debarking logging, and transporting | TFPP16
|  | Tree Felling for ha | TFPP17
|  | User Agency submit application to DFO for taking the posession of felled area with coordinates of same area | TFPP18
|  | DFO Grants permission after field visits by ranger (regular) | TFPP19
| Environment Clearance | Preparation of Prefeasibility Report/Form 1 | EC1
|  | On line Submission of Form 1& Prefeasibility Report | EC2
|  | ToR presentation to EAC | EC3
|  | ToR Granted by MoEF | EC4
|  | Baseline Study | EC5
|  | Draft EIA/EMP preparation | EC6
|  | EIA/EMP Report submission to Member Secretary, SPCB for PH | EC7
|  | Notice for Public Hearing by SPCB | EC8
|  | Conducting Public Hearing | EC9
|  | SPCB Recommendation of public hearing proceeding to MoEF | EC10
|  | Preparation of revised EIA/EMP on the basis of Public Hearing MoM | EC11
|  | Final EIA/ EMP Submission to MoEF | EC12
|  | Review of EIA/EMP by MoEF | EC13
|  | Issue of Date for EC Presentation | EC14
|  | EIA/EMP Presentation to MoEF | EC15
|  | Grant of Environment Clearance by MoEF | EC16
Mining Lease | Mining Lease | Prepare and Submit application for Mining Lease to District Collector/ District Mining Officer | ML1
|  | DGPS Survey of Complete Area | ML2
|  | Obtain NoC from Tehsildar/ DFO/ Gram Panchayats | ML3
|  | Collector recommends the application to Director Geology and Mining (DGM) | ML4
|  | DGM forwards to Secretary MRD (Mineral Resource Department) | ML5
|  | Secretary MRD recommend for prior approval to Central Govt. (Mo | ML6
|  | Issuance of Prior Approval by Central Government (MoC) | ML7
|  | State MRD issues a letter for necessary approval to user agency | ML8
|  | User agency submit the necessary approvals and request for grant o | ML9
|  | Secretary, MRD Grant ML to user agency | ML10
|  | User Agency submit applilcation to collector for execution of ML | ML11
|  | Execute Mining Lease | ML12
Land Acquisition and R & R | Land Acquisition (LARR Act 2013) | Apply to DC u/s 2 (1) of LARR Act, 2013 | LA1
|  | Preliminary investigation for determination of Social Impact& Public Purpose U/S 4(1) | LA2
|  | Issue of Notice by DC for SIA Study u/s 4(1) | LA3
|  | Make 4(1) notification available to Panchayat, Muncipality, DC, SDM | LA4
|  | Publish 4(1) notification in affected area | LA5
|  | Payment for SIA to DC | LA6
|  | Start of Social Impact Assessment Study | LA7
|  | Preparation of SIA/SMP | LA8
|  | Publicity of Public Hearing u/s 5 | LA9
|  | SIA Public Hearing u/s 5 | LA10
|  | Preparation of Final SIA/SMP u/s sec 5 | LA11
|  | Translation of SIA/SMP in Local Language | LA12
|  | Publish SIA/SMP in local Language to Panchayat, Municipality, DC,SDM, Tehsil | LA13
|  | Recommendation by Expert Group u/s 7(6) | LA14
|  | Make Recommendation available (in Local Language) to Panchayat, Muncipality, DC, SDM,Tehsil | LA15
|  | Examination of LA Proposal& SIA/SMP by Govt u/s 8 | LA16
|  | Decision of Govt for LA u/s 8(1) | LA17
|  | Govt Decision to be made available to Panchayat,Muncipality, DC, SDM,Tehsil u/s 8(3) | LA18
|  | Demand Note for compensation and Service Charges | LA19
|  | Deposit of money against demand note | LA20
|  | Publication of Priliminary Notification u/s11 (1) | LA21
|  | Publication in two daily newspaper, Panchayat, District collector, SDM and Tehsil (Local Language) | LA22
|  | Publish 11 (1) in affected area (in Local Language) | LA23
|  | Informed concerned Gram Sabha, Muncipality u/s 11(2) | LA24
|  | Updation of Land Record by Collector u/s 11(5) | LA25
|  | DGPS Survey of Complete Area | LA26
|  | Payment for damage during survey u/s 13 | LA27
|  | Hearing of objection u/s 15 (1) | LA28
|  | Prepare& submit Draft R&R Scheme u/s 16 (u/s 43) | LA29
|  | R&R Scheme Prepared by R&R Administrator | LA30
|  | Publicity of Draft R&R Scheme in affected areas | LA31
|  | Notice for Public Hearing for R&R u/s 16(5) | LA32
|  | Conduct Public Hearing/ Gram Sabha in each village u/s 16(5) | LA33
|  | Submit Draft R&R Scheme to Collector u/s 16(6) | LA34
|  | Review of Draft R&R Scheme by collector and submission to Commissioner u/s 17(1) | LA35
|  | Approval of R&R scheme by Commissioner u/s 17(2) | LA36
|  | Publish Approved R&R Scheme in affected area u/s 18 | LA37
|  | Deposit amount in full or part as prescribed | LA38
|  | Publication of Declaration and Summary of R&R by Secretary to gov | LA39
|  | Land Declared u/s 19 (LA 2013) | LA40
|  | Mark and measure the land u/s 20 | LA41
|  | Notice to Person interested u/s 21 | LA42
|  | Hearing of Objections u/s 21 (2) | LA43
|  | Enquiry& Land acquisition award by collector u/s 23 | LA44
|  | Payment of balance amount to Govt. | LA45
|  | Payment Disbursement | LA46
|  | Possession of Land u/s 38 | LA47
|  | R&R Award by collector for PAFs u/s 31(1) | LA48
|  | Constitute R&R committe of Project u/s 45 to monitor and review of progress of R&R | LA49
|  | Quantify and deposit R&R Amount into a account as directed by R&R Administrator u/s 47 | LA50
Other Consent and Clearances | 1Consent to Establish | Application by Project Proponent on online portal | CTE1
|  | Submission of Hard Copy to Member Secretary, SPCB along with the online communication | CTE2
|  | Site Inspection by RO, SPCB& its recommendations | CTE3
|  | Presentation and Appraisal by Technical Committee | CTE4
|  | Grant of CTE | CTE5
|  | Payment of requisite fees by Project Proponenent | CTE6
| Consent to Operate | Application by Project Proponent on online portal | CTO1
|  | Submission of Hard Copy to Member Secretary, SPCB along with the online communication | CTO2
|  | Site Inspection by RO, SPCB& its recommendations | CTO3
|  | Presentation and Appraisal by Technical Committee | CTO4
|  | Grant of CTO | CTO5
DGPS Survey of Complete Area
| Application for Mine Opening to Coal Controller | Grant of Mine Opening Permission
| Application to DGMS for necessary permissions | Permission for Deployment of HEMM
| Application to CLC | Permission for deployment of contract labour
Notice regarding industrial unit
| Opening of Escrow Account | Opening of Escrow Account
| Mine Operation | Notice to DGMS regarding Mine opening
Notice to Collector and other regarding mine opening
Start of Box cut
Intimation of actual date of start of mine to DGMS and Collector

## Partner Onboarding
Milestone | Sub-Milestone | Activities | Activity Code | Key Milestones Flag | Target Start Date-Aggressive | Target Start Date - Realistic | Duration-Aggressive | Duration - Realistic | Target Finish Date - Aggressive | Target Finish Date - Realistic | Duration | Actual Start Date | Actual Completion Date | Status | POC | Remark
Tendor- Mining Plan | Uploading of NIT | Preparation and vetting of RFP documents | T1 | [10 empty] | Completed | PPD
Tendor- Mining Plan | Uploading of NIT | Approval of tender documents | T2 | [10 empty] | Completed | PPD
Tendor- Mining Plan | Uploading of NIT | Uploading of NIT | T3 | [10 empty] | Completed | PPD
Tendor- Mining Plan | Uploading of corrigendum | Pre-bid meeting | T4 | [10 empty] | Completed | PPD
Tendor- Mining Plan | Uploading of corrigendum | Preparation of responses | T5 | [10 empty] | Completed | PPD
Tendor- Mining Plan | Uploading of corrigendum | Approval of responses | T6 | [10 empty] | Completed | PPD
Tendor- Mining Plan | Uploading of corrigendum | Uploading of corrigendum | T7 | [10 empty] | Completed | PPD
Tendor- Mining Plan | Evaluation of bids | Bid submission | T8 | 1 |  |  |  |  | 2023-07-06 | 2023-07-06 |  |  |  | Completed | PPD | Only 1 Bid arrived
Tendor- Mining Plan | Evaluation of bids | Technical Evaluation | T9 | [5 empty] | 2023-07-13 | 2023-07-13 |  |  |  | Yet to be started | PPD + GEO
Tendor- Mining Plan | Evaluation of bids | Approval for opening of IPO | T10 | [5 empty] | 2023-07-18 | 2023-07-20 |  |  |  | Yet to be started | PPD + GEO
Tendor- Mining Plan | Issue LoA to shirtlisted Agency | Shortlisting preferred agencies | T12 | [5 empty] | 2023-07-20 | 2023-07-27 |  |  |  | Yet to be started | PPD + GEO
Tendor- Mining Plan | Issue LoA to shirtlisted Agency | Final round of negotiations | T12 | [5 empty] | 2023-07-22 | 2023-08-03 |  |  |  | Yet to be started | PPD + GEO
Tendor- Mining Plan | Issue LoA to shirtlisted Agency | Issue LoA to shirtlisted Agency | T12 | 1 |  |  |  |  | 2023-07-25 | 2023-07-28 |  |  |  | Yet to be started | PPD + GEO
Tendor- EC + FC | Uploading of NIT | Preparation and vetting of RFP documents | T1 | [10 empty] | Completed | PPD
Tendor- EC + FC | Uploading of NIT | Approval of tender documents | T2 | [10 empty] | Completed | PPD
Tendor- EC + FC | Uploading of NIT | Uploading of NIT | T3 | [10 empty] | Completed | PPD
Tendor- EC + FC | Uploading of corrigendum | Pre-bid meeting | T4 | [10 empty] | Completed | PPD
Tendor- EC + FC | Uploading of corrigendum | Preparation of responses | T5 | [10 empty] | Completed | PPD
Tendor- EC + FC | Uploading of corrigendum | Approval of responses | T6 | [10 empty] | Completed | PPD
Tendor- EC + FC | Uploading of corrigendum | Uploading of corrigendum | T7 | [10 empty] | Completed | PPD
Tendor- EC + FC | Evaluation of bids | Bid submission | T8 | 1 |  |  |  |  | 2023-07-20 | 0 |  |  |  | In-progress | PPD
Tendor- EC + FC | Evaluation of bids | Technical Evaluation | T9 | [5 empty] | 2023-07-27 | 1900-01-06 |  |  |  | Yet to be started | PPD + ENV
Tendor- EC + FC | Evaluation of bids | Approval for opening of IPO | T10 | [5 empty] | 2023-08-01 | 1900-01-13 |  |  |  | Yet to be started | PPD + ENV
Tendor- EC + FC | Issue LoA to shirtlisted Agency | Shortlisting preferred agencies | T12 | [5 empty] | 2023-08-03 | 1900-01-20 |  |  |  | Yet to be started | PPD + ENV
Tendor- EC + FC | Issue LoA to shirtlisted Agency | Final round of negotiations | T12 | [5 empty] | 2023-08-05 | 1900-01-27 |  |  |  | Yet to be started | PPD + ENV
Tendor- EC + FC | Issue LoA to shirtlisted Agency | Issue LoA to shirtlisted Agency | T12 | 1 |  |  |  |  | 2023-08-12 | 1900-02-10 |  |  |  | Yet to be started | PPD + ENV
Tendor- DPR | Uploading of NIT | Preparation and vetting of RFP documents | T1
Tendor- DPR | Uploading of NIT | Approval of tender documents | T2
Tendor- DPR | Uploading of NIT | Uploading of NIT | T3
Tendor- DPR | Uploading of corrigendum | Pre-bid meeting | T4
Tendor- DPR | Uploading of corrigendum | Preparation of responses | T5
Tendor- DPR | Uploading of corrigendum | Approval of responses | T6
Tendor- DPR | Uploading of corrigendum | Uploading of corrigendum | T7
Tendor- DPR | Evaluation of bids | Bid submission | T8
Tendor- DPR | Evaluation of bids | Technical Evaluation | T9
Tendor- DPR | Evaluation of bids | Approval for opening of IPO | T10
Tendor- DPR | Evaluation of bids | IPO opening and reverse auction | T11
Tendor- DPR | Issue LoA to shirtlisted Agency | Shortlisting preferred agencies | T12
Tendor- DPR | Issue LoA to shirtlisted Agency | Final round of negotiations | T12
Tendor- DPR | Issue LoA to shirtlisted Agency | Issue LoA to shirtlisted Agency | T12
Tendor- MDO | Onboarding a transaction Advisory | Float RFP to onboard a transaction advisory | T1
Tendor- MDO | Onboarding a transaction Advisory | Onboard transaction advisory | T2
Tendor- MDO | Uploading of NIT | Preparation and vetting of RFP documents | T4
Tendor- MDO | Uploading of NIT | Approval of tender documents | T5
Tendor- MDO | Uploading of NIT | Uploading of NIT | T6
Tendor- MDO | Uploading of corrigendum | Pre-bid meeting | T7
Tendor- MDO | Uploading of corrigendum | Preparation of responses | T8
Tendor- MDO | Uploading of corrigendum | Approval of responses | T9
Tendor- MDO | Uploading of corrigendum | Uploading of corrigendum | T10
Tendor- MDO | Evaluation of bids | Bid submission | T11
Tendor- MDO | Evaluation of bids | Technical Evaluation | T12
Tendor- MDO | Evaluation of bids | Approval for opening of IPO | T13
Tendor- MDO | Evaluation of bids | IPO opening and reverse auction | T14
Tendor- MDO | Issue LoA to shirtlisted Agency | Shortlisting preferred agencies | T15
Tendor- MDO | Issue LoA to shirtlisted Agency | Final round of negotiations | T16
Tendor- MDO | Issue LoA to shirtlisted Agency | Issue LoA to shirtlisted Agency | T17
Tendor- Land Acquisition and R&R | Uploading of NIT | Preparation and vetting of RFP documents | T1 | [10 empty] | Completed | PPD
Tendor- Land Acquisition and R&R | Uploading of NIT | Approval of tender documents | T2 | [10 empty] | Completed | PPD
Tendor- Land Acquisition and R&R | Uploading of NIT | Uploading of NIT | T3 | [10 empty] | Completed | PPD
Tendor- Land Acquisition and R&R | Uploading of corrigendum | Pre-bid meeting | T4 | [10 empty] | Completed | PPD
Tendor- Land Acquisition and R&R | Uploading of corrigendum | Preparation of responses | T5 | [10 empty] | Completed | PPD
Tendor- Land Acquisition and R&R | Uploading of corrigendum | Approval of responses | T6 | [10 empty] | Completed | PPD
Tendor- Land Acquisition and R&R | Uploading of corrigendum | Uploading of corrigendum | T7 | [10 empty] | Completed | PPD
Tendor- Land Acquisition and R&R | Evaluation of bids | Bid submission | T8 | 1 |  |  |  |  | 2023-07-12 | 0 |  |  |  | In-progress | PPD
Tendor- Land Acquisition and R&R | Evaluation of bids | Technical Evaluation | T9 | [5 empty] | 2023-07-19 | 1900-01-06 |  |  |  | Yet to be started | PPD + Land Cell
Tendor- Land Acquisition and R&R | Evaluation of bids | Approval for opening of IPO | T10 | [5 empty] | 2023-07-24 | 1900-01-13 |  |  |  | Yet to be started | PPD + Land Cell
Tendor- Land Acquisition and R&R | Issue LoA to shirtlisted Agency | Shortlisting preferred agencies | T12 | [5 empty] | 2023-07-26 | 1900-01-20 |  |  |  | Yet to be started | PPD + Land Cell
Tendor- Land Acquisition and R&R | Issue LoA to shirtlisted Agency | Final round of negotiations | T12 | [5 empty] | 2023-07-28 | 1900-01-27 |  |  |  | Yet to be started | PPD + Land Cell
Tendor- Land Acquisition and R&R | Issue LoA to shirtlisted Agency | Issue LoA to shirtlisted Agency | T12 | 1 |  |  |  |  | 2023-08-04 | 1900-02-10 |  |  |  | Yet to be started | PPD + Land Cell
Formulas:
Target Finish Date - Aggressive = [Target Finish Date - Aggressive, row above]+7
Target Finish Date - Realistic = [Target Finish Date - Realistic, row above]+7
Target Finish Date - Realistic = [Target Start Date - Realistic]

## Support Activities
Milestone | Sub-Milestone | Activities | Activity Code | Key Milestones Flag | Target Start Date | Target Finish Date | Duration | Actual Start Date | Actual Completion Date | Status | POC | Remark
Guest house - BBSR
Office Space - BBSR
Guest house - BW
Office Space - BW
Guest house - BP
Office Space - BP
Hiring of Odisha Project Team
Vehicle procurement
CSR Activities - BW
CSR Activities - BP
IT Infra and connectivity setup
Logistics pe-feasibility study

## HO Core Team
Key Milestones/Activities | Project/Dept. Mentor | Project Co-ordinators | BCG Co-ordinator | Department Owner/ POC | Key Roles & Responsibility | MOC Deadline |  | Penalty Amount (INR Cr) |  | Progress made so far… | Key task in next 4 weeks…
[6 empty] | Baitarni West | Burapahar | Baitarni West | Burapahar
Mine Plan Preparation & Approval | H K Joshi | 1.Swagat Ray | 1.Ravinder Yadav | Piyush Shah | 1.Extension of current role & responsibilty to support operationalization of coal blocks ahead of timelines. Key responsibilities involve regularly interacting with designated agencies to get the studies/assessments done on ground , liason with internal/external stakeholders to ensure all activities are completed within set timelines 2. This is a time bound work,precise planning may be done by Owner POC to avoid any delay.There will be huge penalty for any delay beyond stipulated timeline set by MOC. | Already approved | 2023-12-07 |  | 53.1747 | 1. Roll-out of RFP to onboard agency , conducted pre-bid meeting and uploaded reply to queries online (BP) Last date of bid submission : 6th July 2023 | 1. Secure Mine plan and mine closure plan from OMC ( BW ) 2. Secure GR from CMPDIL ( BP) 3. Onboarding agencies for mining plan preparation ( BP ) 4. Support in drafting RFP for preparing DPR ( BP + BW ) 5. Securing login credentials for SWCS portal
|  | 2.B K Mahato | 2. Anurag Khandelwal
3.Devesh Srivastav
4 D K Thakkar
Environment & Forest clearance | H K Joshi | 1.Swagat Ray | 1.Ravinder Yadav | 1.Dr Ajay Mehrotra |  | 2024-12-07 | 2025-06-07 | 110.5 | 53.1747 | 1. Roll-out of RFP to onboard agency , conducted pre-bid meeting and uploaded reply to queries online (BP) Last date of bid submission : 20th July 2023 | 1. Onboarding agencies for mining plan preparation ( BP + BW) 2. Initiate process to secure draft EIA report from CMPDIL ( BW ) - to be discussed internally 3. Initiate conversation with OMC to get access to CA land allocated to BW - to be discussed internally
| A K Makadia | 2.B K Mahato | 2. Anurag Khandelwal | 2.Dr Gurdeep Singh
3.Devesh Srivastav
4 D K Thakkar
Land acquisition and R & R | H K Joshi | 1.Swagat Ray | 1.Ravinder Yadav | Piyush Shah |  | 2026-09-07 | 2027-03-07 | 276.3 | 132.9369 | 1. Roll-out of RFP to onboard agency , conducted pre-bid meeting and uploaded reply to queries online (BP) Last date of bid submission : 12th July 2023 | 1. Onboarding agencies for Land Acquisition and R&R ( BP + BW) 2. Source Gazette notification u/s 11(1) CBA Acr , 1957 - Land measuring 1192.2930 Ha and all rights in or over the said land vested to OMC (BW)
| Rajat Dash | 2.B K Mahato | 2. Anurag Khandelwal
3.Devesh Srivastav
4 D K Thakkar
Mine opening permissions | H K Joshi | B K Mahato | 1.Ravinder Yadav | B K Mahato / GM-Batarni / GM-Burapahar |  | 2027-03-07 | 2027-09-07 | 276.3 | 132.9369
Manpower - Hiring | H K Joshi | B K Mahato | 1.Ravinder Yadav | S D Bhandari |  | Phased timelines | Phased timelines |  |  | Initiated hiring for : 1.Appointment order issued to Head Project Planning & Adminisratio (BW & BP). 2.Interview completed for Head Project Planning & Adminisration -RCO office BBSR. 3.Shortlisted GM (Project) & DGM(Coal) candidates for BW & BP. | Initiate hiring for : 1. Interview and appointment for General Manager (Project) & DGM (Coal). - BW + BP 2. Re-invite application for DGM (A/C) & DGM(CC) 3. Initiate process for hiring of other position after approval of organogram from competent authority.
2. Anurag Khandelwal
Marketing, Sales & Logistic | H K Joshi | B K Mahato | 1.Ravinder Yadav | Rajat Dash |  | Phased timelines | Phased timelines |  |  | 1. Initaited customer discovery sessions for customers in Odisha + nearby states 2. Initiated customer discovery sessions for coastal demand centers ( including Gujarat) 3. Shortlisted agencies to conduct pre-feasibility assessment of evacuation routes ( Rail / Road / Sea ) | 1. Continue customer discovery sessions ( Odisha + Coastal) 2. Evaluate potential in export market as well
2. Anurag Khandelwal
Power Expansion | H K Joshi | B K Mahato | 1.Ravinder Yadav | Janardan Dave |  | Phased timelines | Phased timelines |  |  | 1. Completed pre-feasibility study of setting a pithead power plant at mine sites 2. Assessed feasibility of servicing Gujarat from pithead plant | 1. Assess customers to shortlist priority customers for reach out 2. Assess stressed assets for partner / customer discussions
2. Anurag Khandelwal
Finance | L. Kulshrestha | B K Mahato | 1.Ravinder Yadav | Anupama Iyer |  | Phased timelines | Phased timelines |  |  | 1. Submitted fixed payment and BG as per timelines to MOC | 1. Support with all future capital disburesements and payment to MOC
| H K Joshi |  | 2. Anurag Khandelwal